## Slide 1: ENI CBC Project development: building the project intervention logic and logical framework approach
ENI capacity building workshops for project applicants in Republic of Moldova
19 March 2018, Cahul
21 March 2018, Comrat
23 and 24 March 2018, Chisinau
26 March 2018, Balti

## Slide 2
Scope
Time
Budget
Time
Within a given period
Scope
In order to achieve predefined goals
Budget/Cost
Implemented with limited resources
  Combination of planned activities
Risk & Quality
Project key elements
Notes: The main idea of this slide is that a project has 3 mutually limitative elements: scope, budget and time. E.g. given a certain budget, if I increase scope, I have to reduce the time. That is, touching one of them necessarily affects the others.

## Slide 3
Identification of project Ideas
Analysis of the Project Idea
Planning / Proposal
Financing
Implementation
Monitoring
Project Cycle Management

## Slide 4: WHY?

## Slide 5
WHY do you do what you do? What is the purpose?
HOW do you do what you do?
So, WHAT will you do?
GOLDEN CIRCLE – Idea by Simon Sinek

## Slide 6
Developing a Logical Framework Matrix – assessing consistency among different components of the project, risks / assumptions and define objectively verifiable performance indicators
Activity Planning – define activities, time / scope / who / when / what / how
Resource Planning – human resources and budget
Problem Analysis – Identification of important problems and causal relationship among all problems
Stakeholder Analysis – Identification of all the stakeholders of the project
Objective Analysis – Provide solutions to the defined problems of the project
Strategy Analysis – develop strategies to tackle the problems identified
Planning
Analysis
Logical Framework Approach

## Slide 7: What do you want to improve? Which is the situation needing a change?

## Slide 8
WHICH ARE THE PROBLEMS?
  Problem analysis is the initial stage of project identification:
    your project will adress a common problem (e.g. cross-border water pollution) or a missed opportunity (e.g. limited access to external markets),
    the situation should be improved at the end of the project as compared to before!
  Check that the problem has a cross-border dimension related to the programme priorities!
Problem analysis

## Slide 9
WHICH ARE THE PROBLEMS?
It is not enough to state there is a problem, you should analyse its causes and related effects
  Describe first the negative situation and do not start straight away finding the solution to the problem, there are usually several ways to solve a problem!
  You need to get an overview of all causes of the problem, though you will only target some of them in your project (other may need to be included in project external risks and assumptions)
Problem analysis

## Slide 10
Problem analysis: building the problem “tree”
CAUSES
EFFECTS

## Slide 11: Who’s affected by the negative situation?

## Slide 12
Stakeholder analysis
 | WHOSE PROBLEM IS IT?
Analyse who’s affected | directly or indirectly – by the problem or have an interest in it: individuals, groups of people, institutions or firms (local authorities, environment agency, farmers…) = stakeholders
Check cross-border dimension | are there stakeholders in several countries of the ENI MED?
Analyse the impact of the problem on various stakeholders | different groups have different concerns, capacities and interests (sometimes conflicting) - these need to be understood and recognized in the process of problem identification
Consult stakeholders | from the beginning and throughout project design!

## Slide 13: What could be the improved situation? Which is the change you want to get?

## Slide 14
Objective analysis
WHAT ARE THE OBJECTIVES?
  Negative situations of the problem tree converted into positive achievements = objectives
  Methodological approach to:
  Get an overview of the desired future situation (when all problems are remedied)
  Illustrate means-ends relationship
  Keep the analysis of potential objectives clearly based on adressing a range of identified priority problems
  Provides the basis for the project strategy analysis!

## Slide 15
Objective analysis: building the “objective tree”
MEANS
ENDS

## Slide 16
Strategy analysis
DEFINING THE SCOPE OF YOUR PROJECT IDEA
  Shall all identified problems/objectives be tackled or only a few?
What objective(s) cannot be reached acting only on a national/regional/local level and needs CBC?
  What can realistically be afforded within the ENI MED call financial limits?
  Will it contribute to programme indicators?
  How does it build upon previous/current/planned actions in this field? Possible complementarities/synergies/overlaps? Scope for replication?

## Slide 17: Let’s practice on problem and objective analysis

## Slide 18
Problem analysis – group work (per priority)
Brainstorm main cross border problems related to the priority and select one individual focal problem | write on yellow card
Identify related problems to this focal problem | write on yellow cards
Establish hierarchy of causes and effects | stick accordingly the cards on the flipchart paper and draw arrows from causes to effects
Identify who’s affected by each problem | write on pink cards and stick next to each related problem
A problem is not the absence of a solution, but a negative situation | e.g. “crops are infested with pests” is a problem, “no pesticides are available” is not)!

## Slide 19
Objective analysis – group work (per priority)
Reformulate all negative situations of the problems analysis into positive situations that are desirable and realistically achievable | write on green cards Organise on the flipchart paper accordingly at the same line as appropriate problem
Check the means-ends relationships to ensure validity and completeness of the hierarchy: | if necessary revise statements, add new objectives (means) if relevant to achieve the objective at the next higher level, delete objectives which do not seem suitable or necessary
Assess impact on stakeholders (positive-negative, involvement realistic?) - | write on pink cards and stick next to the related objective

## Slide 20
Application form
Intervention logic
Results chain
The intervention logic
outputs
results
impact
activities
WHICH ARE THE NECESSARY RESOURCES FOR CARRYING OUT THE ACTIVITIES?
WHY I AM PROPOSING THIS PROJECT?
general objective
WHAT DO I WANT TO CHANGE?
specific objectives and results
WHAT WILL I GET FROM THE PROJECT?
outputs
HOW I AM GOING TO GET THE OUTPUTS?
activities
inputs
budget, time, Premises, etc.

## Slide 21
Setting project objectives in a logical way
High levels of solid waste dumped into the river
River water quality is deteriorating
No public information or education programs available
Population not aware of the danger of waste dumping
Public information/ education programs established
Population more aware of the danger of waste dumping
The quantity of solid waste dumped into the river is reduced
River water quality is improved
PROBLEMS
OBJECTIVES
PROJECT INTERVENTION LOGIC LEVELS
Broader long-term change to which the project contributes
Linked to a programme priority
What the project aims to achieve
Direct short-term and medium-term effects of the outputs
Tends to focus on changes in behaviour resulting from the outputs
Services, goods, infrastructure that are produced/delivered by the project activities
Impact
Result
Intermediary result
Output
Notes: Note to trainer:
There are 4 basic levels in a logical framework. Whatever the template, the definition of each level is always very similar. However, the terminology used for these 4 levels evolves over time and organisations, which is likely to create some confusion among applicants/partners and evaluators/assessors.
In the slides used in this training we follow a terminology that is consistent with the ENI CBC Implementing Rules and the ENI CBC Programming Document. Note however that this is not fully consistent with PraG current terminology (inserted in brackets).
There are 4 basic levels in the design of a project logic of intervention. At the lowest level you define what you will do, these are your project activities. For instance, you will train, design, publish, etc. These operations require the utilisation of both material and human resources – these are called inputs . These activities will produce or deliver services, goods and/or infrastructure: these are usually called the project outputs The project will be held accountable for producing the outputs, so be very careful in defining and quantifying these. The outputs are the building blocks of the project; they should provide the conditions necessary to achieve the project higher results
The project higher result level, also often called outcome or specific objective level, specifies what the project aims to achieve. This level focuses on the short-term and medium-term effects of the project outputs, it identifies what will change, notably in behaviours, and who will benefit as a direct result of the project
Remember that the project by itself is expected to achieve the defined results.
At the top, you will identify what is the broader long-term effect to which your project, along with others, contributes – this is the impact, or overall objective, level . It should indicate relevance to the programme by being directly linked to a programme priority .
There should be a logical link between your activities, outputs, results and impacts: your activities must produce or deliver something
To produce an infrastructure or deliver goods and services that is of use to nobody is also absurd: your outputs should lead to a positive change for someone, preferably for many people : these will be your project target groups. Eventually, your results should contribute to a broader, positive change to which the cross-border cooperation programme aspires when funding your project – it will improve the lives of your project’s final beneficiaries
Other important aspects to integrate in your project intervention are the project management and communication issues. Make sure to include relevant communication activities, both internal to ensure a smooth coordination and dialogue among partners, and external to make your project outputs and results visible and possibly replicable by others. Think also about the sustainability of your outputs and results, this has to be built in from the beginning of project design.
  As project partners tend to jump too quickly into thinking of doing something rather than thinking of achieving something and then sometimes lose track of their broader strategy, we strongly encourage you to build your project intervention logic starting from the objectives

## Slide 22
PROJECT INTERVENTION LOGIC/ENI MED APPLICATION FORM (AF)
The general objective shall contribute to the Programme strategy
What does the project want to achieve in relation to the addressed Programme Priority?
Services, goods, infrastructure that are produced/delivered by the project activities
Impact (overall objective)
Change (specific objectives)
Result
Output
Explain the change you want to bring to tackle the identified needs/challenges
Notes: Note to trainer:
There are 4 basic levels in a logical framework. Whatever the template, the definition of each level is always very similar. However, the terminology used for these 4 levels evolves over time and organisations, which is likely to create some confusion among applicants/partners and evaluators/assessors.
In the slides used in this training we follow a terminology that is consistent with the ENI CBC Implementing Rules and the ENI CBC Programming Document. Note however that this is not fully consistent with PraG current terminology (inserted in brackets).
There are 4 basic levels in the design of a project logic of intervention. At the lowest level you define what you will do, these are your project activities. For instance, you will train, design, publish, etc. These operations require the utilisation of both material and human resources – these are called inputs . These activities will produce or deliver services, goods and/or infrastructure: these are usually called the project outputs The project will be held accountable for producing the outputs, so be very careful in defining and quantifying these. The outputs are the building blocks of the project; they should provide the conditions necessary to achieve the project higher results
The project higher result level, also often called outcome or specific objective level, specifies what the project aims to achieve. This level focuses on the short-term and medium-term effects of the project outputs, it identifies what will change, notably in behaviours, and who will benefit as a direct result of the project
Remember that the project by itself is expected to achieve the defined results.
At the top, you will identify what is the broader long-term effect to which your project, along with others, contributes – this is the impact, or overall objective, level . It should indicate relevance to the programme by being directly linked to a programme priority .
There should be a logical link between your activities, outputs, results and impacts: your activities must produce or deliver something
To produce an infrastructure or deliver goods and services that is of use to nobody is also absurd: your outputs should lead to a positive change for someone, preferably for many people : these will be your project target groups. Eventually, your results should contribute to a broader, positive change to which the cross-border cooperation programme aspires when funding your project – it will improve the lives of your project’s final beneficiaries
Other important aspects to integrate in your project intervention are the project management and communication issues. Make sure to include relevant communication activities, both internal to ensure a smooth coordination and dialogue among partners, and external to make your project outputs and results visible and possibly replicable by others. Think also about the sustainability of your outputs and results, this has to be built in from the beginning of project design.
  As project partners tend to jump too quickly into thinking of doing something rather than thinking of achieving something and then sometimes lose track of their broader strategy, we strongly encourage you to build your project intervention logic starting from the objectives

## Slide 23: What will you do?

## Slide 24
Defining activities to produce outputs & achieve results
1
1.1
1.1.1
1.1.2
1.2
1.2.1
Result
Outputs
Activities
1.1.3
1.2.2

## Slide 25
Strategy analysis: what needs to be done and how?
DEFINING THE SCOPE OF YOUR CBC PROJECT ACTIVITIES
  Do they take into account programme cross-cutting issues (e.g. gender)?
  What can realistically be afforded within the call financial limits?
  Will the activities produce project outputs that are sustainable?
  What about communication and management/ coordination ?
Are they eligible under the programme rules?
  Will it contribute to ENI MED programme priorities?

## Slide 26: Who do you do the project for? Who do you consult and involve?

## Slide 27
Stakeholders analysis
Stakeholders
Who will benefit?
Who will loose out?
Directly (target groups)
Indirectly/in the long term (final beneficiaries)
What is their capacity and motivation to bring a change?
What are possible actions to address their needs and interest?
Gender relevance?
1.5 Target groups, final beneficiaries and needs
Describe and quantify your target groups and final beneficiaries. Explain how and why they were identified and involved in the project preparation. Detail their needs and how they will be addressed by the project.
From application form

## Slide 28
Who will be affected by the project or can affect it?
TARGET GROUPS
Who will benefit directly from the outputs and result(s) of the project (e.g. inhabitants, farmers , property owners etc)
Those directly involved in the activities (e.g. local authorities, environmental agencies, farmers association…)
FINAL BENEFICIARIES
Who will benefit indirectly or in the long term from the project (e.g. population living on the riverside, farmers, …)
activities
outputs
results
impact
STAKEHOLDERS
Persons or organisations that can affect or be affected (positively/negatively) by the project (e.g. local authorities, environmental protection agency, industry, other donors…)
Notes: With the animation first appears the 3 words: final beneficiaries, target groups and stakeholders and, again, ask the participants to explain the difference and relation to intervention logic.
First question: what are stakeholders? Different types of stakeholders (so they find who’s missing in the 2 « boxes ») then make appear target groups & beneficiaries titles.
When have defined them all, definitions appear
Remind them that some stakeholders can also be negatively affected by the project (eg industry polluters in case of environmental project – cannot be ignored, also need be integrated in project strategy)

## Slide 29
Who will be affected by the project or can affect it?
TARGET GROUPS
Who will benefit directly from the outputs and result(s) of the project (e.g. farmers, environmental NGOs and officials...
Those directly involved in the activities (e.g. property owners, environmentalists, farmer association…)
FINAL BENEFICIARIESالمستفيدين النهائيين
Who will benefit indirectly or in the long term from the project (e.g. inhabitants from Alavir&Rivala region, fishermen...)المستفيدين بشكل غير مباشر او على المدى الطويل من المشروع(على سبيل المثال، والناس من منطقتي ألافير وريفالا والصيادين ...)
activities
outputs
results
Impact
STAKEHOLDER Persons or organisations that can affect or be affected (positively/negatively) by the project (e.g. farmers, local authorities, environmental protection agency…)
FINAL BENEFICIARIES
Who will benefit indirectly or in the long term from the project (e.g. inhabitants from Alavir&Rivala region, fishermen...)
Notes: With the animation first appears the 3 words: final beneficiaries, target groups and stakeholders and, again, ask the participants to explain the difference and relation to intervention logic.
First question: what are stakeholders? Different types of stakeholders (so they find who’s missing in the 2 « boxes ») then make appear target groups & beneficiaries titles.
When have defined them all, definitions appear
Remind them that some stakeholders can also be negatively affected by the project (eg industry polluters in case of environmental project – cannot be ignored, also need be integrated in project strategy)

## Slide 30
Can the project deliver? Check the intervention logic
PROJECT LOGIC OF INTERVENTION
IMPACTS
RESULTS
OUTPUTS
ACTIVITIES
    TOP-DOWN LOGIC:
    Project applicants/partners
    should start from what they want to achieve, until defining what needs to be done
    BOTTOM-UP LOGIC: Evaluators/assessors
    check whether project intervention logic is complete and accurate: will the activities lead to the outputs, the outputs to the results and the results to the expected impact, that contributes to the programme strategy?
Notes: Notes to trainer:
Ask the participants first if they can explain both top-down and bottom-up approaches and who uses them, before you make the boxes appear
The 1st column sets the basic project intervention logic, according to a vertical logical relationship. It is also called the “results chain”.

## Slide 31: Now let’s consider what can go wrong? On top of financing, what is needed so that the project achieves the positive change?

## Slide 32
What are the assumptions (external conditions) & potential risks?
    What factors outside the project management control may prevent the project from delivering its outputs, achieving its result(s) and some impact?
 | Assumptions (external conditions)
Impact | 
Result(s) | What key assumption(s) should hold true so that the result(s) contribute to the impact?
Outputs | What key assumption(s) should hold true so that the outputs achieve the result(s)?
Activities | What key assumption(s) should hold true so that the activities produce the outputs?
Section 2.2 AF

## Slide 33
Are assumptions relevant? Review of external factors
Yes
Is this factor important?
Will it hold true?
Is it possible to redesign the project?
Very unlikely
Possibly
Almost certainly
Yes
No
exclude
exclude
include
No
killing assumption
redesign
Notes:     Note to trainer:
    Reminder on how to advise projects on taking external factors into account

## Slide 34: How will you know what the project achieves?
Notes: Note to trainers:

## Slide 35
Indicators: defining and monitoring progress
 | Intervention logic: rationale | Indicators | Targets (ref. year) | Assumptions
Impact (overall obj.) |  |  |  | 
Result (specific obj.) |  |  |  | 
Outputs |  |  |  | 
Activities |  | Means: Costs: |  | 
When your project design is completed, you need to think about how you will know that your project delivers and achieves as planned.
  To check this, you will need so-called indicators, that is, verifiable description of your outputs, results and impacts in terms of quality, quantity, place and time of performance).
  The indicators will help in monitoring the project results achievements

## Slide 36
LF matrix: indicators (Section 2.1 AF)
 | Intervention logic: | Indicators | Targets (ref. year) | Assumptions
Impact |  |  |  | 
Result (specific obj.) |  | You have to choose from the Programme results indicators for the selected priority | Quantify the project target values | 
Outputs |  | You have to propose your project outputs associated to the Programme outputs for the selected priority | Quantify your own target values | 
Activities |  | (Costs= Budget) |  | 
Notes: Note to trainer:
No indicators are requested at impact level in the MSB call

## Slide 37: Good luck with your project development! AND Please Visit http://www.goforenicbc.eu